Strategy and Plan for HHV Green Future (working title)

|  | 2021 Q3 and Q4 | 2022 | 2023 | 2024 | 2025 |
| --- | --- | --- | --- | --- | --- |
| People | Convene group of vols and advisors Engage with vol from each PCC Identify/Liaise with village PC/groups Liaise with schools | Encourage group of vols Enable 4 schools groups to visit and be involved in nearest church | Develop links with PC green champions |  |  |
| Policy | HHV policy draft (by October): Teaching/energy/building and land use /biodiversity/food/transport/recycling | Adopt by Jan 2022 | Review |  | Consider offsetting |
| Plans | Each church to have draft plan end year as result of liaison and audit; | Partner with village & school plans; develop further with audit results | Review carbon reductions; Update 5 year plan |  | Are we halfway? |
| Actions | Establish baseline carbon footprint for each church 5 x EFT; 7x Eco Church audits Organise biodiversity surveys Template churchyard management plans | 3 Village ‘projects’ eg rainwater harvesting; public biodiversity surveys EFT updated in 7/7 7/7 BRONZE ecochurch awards 5/7 Churchyard management plans | 4 village ‘projects’ EFT & plot progress Review eco church audit SILVER 5/7 7/7 churchyard plans |  | SILVER awards by 7/7 |
| Publicity | Living generously (individuals) Parish mags etc/website/other | Celebrate eco awards Case studies & Monthly ‘living generously’ topics | Celebrate eco awards |  |  |

Where are we today (October 2021)

| Church/village | EFT/Energy Sources | Renewable ele (switch) | Ecochurch audit | Biodiversity | People Church, village, PC & school | Projects & Publicity (exemplar/planned) |
| --- | --- | --- | --- | --- | --- | --- |
| Chiselborough | Yes 2019/ Electricity | PCC approved/RT | Dick O’ Neill ( + Annie and Helen) Yes, Silver Award | Not yet - Helen will lead Through 2022 | Richard and Dick; Helen Hawke (SWT) PC: Grant Morley | Parish mag Eco award |
| Middle Chinnock | Sue Bow: EFT 0.6 tonnes p.a. | ? tbc | Hazel Ellis – + PCC Yes, Bronze Award | ? tbc | Zoe G & Sue B PC: Pete White | Parish mag Eco award |
| Montacute | Yes Prev. gas. Electricity | yes | Susan Laycock Yes, Bronze Award | Keith H arranging with SWT, 2022 | Susan, Annie, Sally PC: David Warry School: Heidi Daniel | God’s Acre Display in church (Eco award) Parish mag |
| Norton sub Hamdon | Peter Wilsher and Richard Raven | ? tbc | Peter Willsher ??? received Bronze Award | Not yet | Peter W Ali Templeton PC: NC leading DC :Mike Hewitson School: JCaswell | Old Tennis court land - NC liaising with Dioc Edu. + organise public Consultation. Parish mag |
| Odcombe | Yes, Annie will do EFT; electricity | Yes PCC approved Ruth asap | Yes, Bronze Award Walton family To be printed and displayed | Not yet – SWT approached in ‘19 | Annie & Trevor Walton & family PC: Pete/Deryl (no eco champion yet) | Trail – parable of sower/rewilding 13-15th August; Allotment rainwater harvest confirmed Eco award /newsletter |
| Stoke sub Hamdon | oil/electricity EFT in progress | PCC approved awaiting switch | Annie + Colleen 7 Sept Yes, Bronze Award | Initial walk with Sylvie, Colleen and David Dwyer . Sylvie will run in Spring | Annie contacted Barbara (PC), Mike Hewitson (DC) School: Steve Morton : November visit | Local groups stall Aug 7th; PC Barbara: Allotments rainwater Harvest Eco award |
| West Chinnock | Marilyn and Brian Trust will do. Date tbc | PCC approved awaiting switch | Marilyn Trust Yes, Bronze Award | Yes – informal audit; | David Mangles (& Brian Trust & Caroline Doherty) DC : Oliver Patrick School: awaited | churchyard management plan in preparation Eco award;parish mag |